## User Story
S. No | As a <<type of user>> | I want <<some goal>> | so that <<reason>> | Date introduced | Date considered for implementation | Developer Responsible | Current Status
1 | Physician | Know the work flow of EMR system | Make sure the business logic of the whole system is correct | 2015-02-06 | 2015-02-10 | Yufan Xue | In Progress
2 | Physician | Login | physician can access the system and perform admin related tasks | 2015-02-10 | 2015-02-15 | JingBo | In Progress
3 | Physician | View patients | View patients
4 | Physician | View an EMR | By default, a physician can search view all EMRs of his/her patients. To view the EMR of another patient, the physician should have been given access rights by the primary care of the corresponding physician. |  |  |  | Not Started
5 | Physician | Add an EMR | Pysician can add an EMR for a patient There should be at most only one EMR per patient. A physician can create an EMR for a patient if and only if the physician is the primary care of the patient. |  |  |  | Not Started
6 | Physician | Search an EMR | Search an EMR or a collection of EMRs. |  |  |  | Not Started
7 | Physician | Update EMR of a patient | Updating an EMR should not modify or delete any existing transcription. Instead, it may change the patient's preferences |  |  |  | Not Started
8 | Physician | Add a new trasncription | Add a new trasncription when a patient sees a physician |  |  |  | Not Started
9 | Physician | View an trasncription | View transcription |  |  |  | Not Started
10 | Physician | Add a new prescription | Add a new prescription |  |  |  | Not Started
11 | Physician | View a prescription | View a prescription |  |  |  | Not Started
12 | Physician | Add acceess rights for another physician to a patient's EMR | The physician may choose to give permanent access right or temporary access right. In the latter case, the date and time at which the access right expires must also be indicated. |  |  |  | Not Started
13 | Physician | Delete access rights for another physician to a patient's EMR | The physician may choose to give permanent access right or temporary access right. In the latter case, the date and time at which the access right expires must also be indicated. |  |  |  | Not Started
14 | Admin | Create an accounts for physicians | There must be an administrator (or administrators) for the EMR component who will create the accounts for the physicians. |  |  |  | Not Started
15 | Admin | Delete an account for physicians | An administrator can only add or delete an account for a physician or for another administrator. |  |  |  | Not Started

## Sprints
S.No. | User Story index | Task | Date introduced | Date considered for implementation | Date completed | Developer responsible for | Current Status
1 | 4 | Set up the database | 2015-01-31 |  |  | Yufan xue | In Progress
2 | 4 | Set up web interface |  |  |  |  | Not Started
3 | 4 | Develop DB access methods |  |  |  |  | Not Started
4 | 4 | Develop GUI and front end control |  |  |  |  | Not Started
5 | 4 | Develop back end service |  |  |  |  | Not Started
6 | 4 | Integerate front end and back end |  |  |  |  | Not Started
7 | 4 | Test login code for physician |  |  |  |  | Not Started