## User Story
S. No | As a <<type of user>> | I want <<some goal>> | so that <<reason>> | Date introduced | Date considered for implementation | Developer Responsible | Current Status
1 | Physician | Know the work flow of EMR system | Make sure the business logic of the whole system is correct | 2015-02-06 | 2015-02-10 | Yufan Xue | Finished
2 | Physician | Login | physician can access the system and perform admin related tasks | 2015-02-10 | 2015-02-15 | Yufan Xue | Finished
3 | Physician | View patients | View patients | 2015-02-16 | 2015-02-20 | Yufan Xue | In Progressing
4 | Physician | View an EMR | By default, a physician can search view all EMRs of his/her patients. To view the EMR of another patient, the physician should have been given access rights by the primary care of the corresponding physician. |  |  |  | Not Started
5 | Physician | Add an EMR | Pysician can add an EMR for a patient There should be at most only one EMR per patient. A physician can create an EMR for a patient if and only if the physician is the primary care of the patient. |  |  |  | Not Started
6 | Physician | Search an EMR | Search an EMR or a collection of EMRs. |  |  |  | Not Started
7 | Physician | Update EMR of a patient | Updating an EMR should not modify or delete any existing transcription. Instead, it may change the patient's preferences |  |  |  | Not Started
8 | Physician | Add a new trasncription | Add a new trasncription when a patient sees a physician |  |  |  | Not Started
9 | Physician | View an trasncription | View transcription |  |  |  | Not Started
10 | Physician | Add a new prescription | Add a new prescription |  |  |  | Not Started
11 | Physician | View a prescription | View a prescription |  |  |  | Not Started
12 | Physician | Add acceess rights for another physician to a patient's EMR | The physician may choose to give permanent access right or temporary access right. In the latter case, the date and time at which the access right expires must also be indicated. |  |  |  | Not Started
13 | Physician | Delete access rights for another physician to a patient's EMR | The physician may choose to give permanent access right or temporary access right. In the latter case, the date and time at which the access right expires must also be indicated. |  |  |  | Not Started
14 | Admin | Create an accounts for physicians | There must be an administrator (or administrators) for the EMR component who will create the accounts for the physicians. |  |  |  | Not Started
15 | Admin | Delete an account for physicians | An administrator can only add or delete an account for a physician or for another administrator. |  |  |  | Not Started

## Sprints
S.No. | User Story index | Task | Date introduced | Date considered for implementation | Date completed | Developer responsible for | Current Status
1 | 1 | Look up Medical Record template, find out what Medical Record look like | 2015-02-01 | 2015-02-02 | 2015-02-02 | Yufan xue | Finished
2 | 1 | Case study: a patient visit a physician, get the transcription from the physician | 2015-02-02 | 2015-02-03 | 2015-02-03 | Han chen | Finished
3 | 1 | Based on business logic, build the GUI | 2015-02-03 | 2015-02-09 | 2015-02-09 | Jingbo,Yufan,Han | Finished
4 | 2 | Set up the database | 2015-02-10 | 2015-02-10 | 2015-02-10 | Yufan xue | Finished
5 | 2 | Set up web interface | 2015-02-10 | 2015-02-13 | 2015-02-13 | Han chen | Finished
6 | 2 | Develop DB access methods | 2015-02-10 | 2015-02-13 | 2015-02-13 | Jingbo | Finished
7 | 2 | Develop GUI and front end control | 2015-02-10 | 2015-02-13 | 2015-02-13 | Yufan xue | Finished
8 | 2 | Develop back end service | 2015-02-10 | 2015-02-14 | 2015-02-14 | Yufan xue | Finished
9 | 2 | Integerate front end and back end | 2015-02-10 | 2015-02-15 | 2015-02-15 | Yufan xue | Finished
10 | 2 | Test login code for physician | 2015-02-15 | 2015-02-15 | 2015-02-15 | Han chen | Finished
11 | 3 | Set up the database | 2015-02-16 | 2015-02-16 | 2015-02-16 | Yufan xue | Finished
12 | 3 | Set up web interface | 2015-02-16 | 2015-02-18 |  | Yufan xue | In Progressing
13 | 3 | Develop DB access methods | 2015-02-17 | 2015-02-19 |  | Han Chen | In Progressing
14 | 3 | Develop GUI and front end control | 2015-02-17 | 2015-02-19 |  | JingBo | In Progressing
15 | 3 | Develop back end service | 2015-02-17 | 2015-02-19 |  | Han Chen | In Progressing
16 | 3 | Integerate front end and back end | 2015-02-20 | 2015-02-20 |  | Yufan xue | Not Started
17 | 3 | Test view patient code for physician | 2015-02-20 | 2015-02-20 |  | Yufan xue | Not Started
18 | 4 | Set up the database |  |  |  |  | Not Started
19 | 4 | Set up web interface |  |  |  |  | Not Started
20 | 4 | Develop DB access methods |  |  |  |  | Not Started
21 | 4 | Develop GUI and front end control |  |  |  |  | Not Started
22 | 4 | Develop back end service |  |  |  |  | Not Started
23 | 4 | Integerate front end and back end |  |  |  |  | Not Started
24 | 4 | Test view EMR code for physician |  |  |  |  | Not Started
25 | 5 | Set up the database |  |  |  |  | Not Started
26 | 5 | Set up web interface |  |  |  |  | Not Started
27 | 5 | Develop DB access methods |  |  |  |  | Not Started
28 | 5 | Develop GUI and front end control |  |  |  |  | Not Started
29 | 5 | Develop back end service |  |  |  |  | Not Started
30 | 5 | Integerate front end and back end |  |  |  |  | Not Started
31 | 5 | Test add EMR code for physician |  |  |  |  | Not Started
32 | 6 | Set up the database |  |  |  |  | Not Started
33 | 6 | Set up web interface |  |  |  |  | Not Started
34 | 6 | Develop DB access methods |  |  |  |  | Not Started
35 | 6 | Develop GUI and front end control |  |  |  |  | Not Started
36 | 6 | Develop back end service |  |  |  |  | Not Started
37 | 6 | Integerate front end and back end |  |  |  |  | Not Started
38 | 6 | Test search EMR code for physician |  |  |  |  | Not Started
39 | 7 | Set up the database |  |  |  |  | Not Started
40 | 7 | Set up web interface |  |  |  |  | Not Started
41 | 7 | Develop DB access methods |  |  |  |  | Not Started
42 | 7 | Develop GUI and front end control |  |  |  |  | Not Started
43 | 7 | Develop back end service |  |  |  |  | Not Started
44 | 7 | Integerate front end and back end |  |  |  |  | Not Started
45 | 7 | Test update EMR code for physician |  |  |  |  | Not Started
46 | 8 | Set up the database |  |  |  |  | Not Started
47 | 8 | Set up web interface |  |  |  |  | Not Started
48 | 8 | Develop DB access methods |  |  |  |  | Not Started
49 | 8 | Develop GUI and front end control |  |  |  |  | Not Started
50 | 8 | Develop back end service |  |  |  |  | Not Started
51 | 8 | Integerate front end and back end |  |  |  |  | Not Started
52 | 8 | Test add transcription code for physician |  |  |  |  | Not Started
53 | 9 | Set up the database |  |  |  |  | Not Started
54 | 9 | Set up web interface |  |  |  |  | Not Started
55 | 9 | Develop DB access methods |  |  |  |  | Not Started
56 | 9 | Develop GUI and front end control |  |  |  |  | Not Started
57 | 9 | Develop back end service |  |  |  |  | Not Started
58 | 9 | Integerate front end and back end |  |  |  |  | Not Started
59 | 9 | Test view transcription code for physician |  |  |  |  | Not Started
60 | 10 | Set up the database |  |  |  |  | Not Started
61 | 10 | Set up web interface |  |  |  |  | Not Started
62 | 10 | Develop DB access methods |  |  |  |  | Not Started
63 | 10 | Develop GUI and front end control |  |  |  |  | Not Started
64 | 10 | Develop back end service |  |  |  |  | Not Started
65 | 10 | Integerate front end and back end |  |  |  |  | Not Started
66 | 10 | Test add prescription code for physician |  |  |  |  | Not Started
67 | 11 | Set up the database |  |  |  |  | Not Started
68 | 11 | Set up web interface |  |  |  |  | Not Started
69 | 11 | Develop DB access methods |  |  |  |  | Not Started
70 | 11 | Develop GUI and front end control |  |  |  |  | Not Started
71 | 11 | Develop back end service |  |  |  |  | Not Started
72 | 11 | Integerate front end and back end |  |  |  |  | Not Started
73 | 11 | Test view prescription code for physician |  |  |  |  | Not Started
74 | 12 | Set up the database |  |  |  |  | Not Started
75 | 12 | Set up web interface |  |  |  |  | Not Started
76 | 12 | Develop DB access methods |  |  |  |  | Not Started
77 | 12 | Develop GUI and front end control |  |  |  |  | Not Started
78 | 12 | Develop back end service |  |  |  |  | Not Started
79 | 12 | Integerate front end and back end |  |  |  |  | Not Started
80 | 12 | Test Add acceess rights for another physician to a patient's EMR code for physician |  |  |  |  | Not Started
81 | 13 | Set up the database |  |  |  |  | Not Started
82 | 13 | Set up web interface |  |  |  |  | Not Started
83 | 13 | Develop DB access methods |  |  |  |  | Not Started
84 | 13 | Develop GUI and front end control |  |  |  |  | Not Started
85 | 13 | Develop back end service |  |  |  |  | Not Started
86 | 13 | Integerate front end and back end |  |  |  |  | Not Started
87 | 13 | Test delete acceess rights for another physician to a patient's EMR code for physician |  |  |  |  | Not Started
88 | 14 | Set up the database |  |  |  |  | Not Started
89 | 14 | Set up web interface |  |  |  |  | Not Started
90 | 14 | Develop DB access methods |  |  |  |  | Not Started
91 | 14 | Develop GUI and front end control |  |  |  |  | Not Started
92 | 14 | Develop back end service |  |  |  |  | Not Started
93 | 14 | Integerate front end and back end |  |  |  |  | Not Started
94 | 14 | Test Create an accounts for physicians EMR code for physician |  |  |  |  | Not Started
95 | 15 | Set up the database |  |  |  |  | Not Started
96 | 15 | Set up web interface |  |  |  |  | Not Started
97 | 15 | Develop DB access methods |  |  |  |  | Not Started
98 | 15 | Develop GUI and front end control |  |  |  |  | Not Started
99 | 15 | Develop back end service |  |  |  |  | Not Started
100 | 15 | Integerate front end and back end |  |  |  |  | Not Started
101 | 15 | Test Delete an accounts for physicians EMR code for physician