## Slide 1: Risk Management

## Slide 2: Risk - Definition
The likelihood of an event, hazard, threat or situation occurring and its undesirable consequences; a potential problem
        IEEE Standard 1540-2001
        Standard for Software Life Cycle Processes – Risk Management

## Slide 3: Risks in Software Development
Action or event that may or may not occur; if occurs, it has a harmful or negative effect on the product
There is a definite uncertainty in the occurrence of a risk
Because of the uncertainty, treating or managing risks is a risky process by itself
If desired to handle risks, it must be planned well ahead (during project planning)

## Slide 4: Examples
Not a risk | Risk
Errors found during system testing or acceptance testing | Incompatibility with external tools or resources
Minor changes in requirements | Reduction of technical staff during development
Addition of new requirements after design | System crash due to hardware failure
Change in management policies (may be a risk) | Budget cut or reduction in resources

## Slide 5: Risks and their consequences
A risk is a probabilistic event
  If occurs, it will have a harmful or negative effect
  If does not occur, it will not have any consequences
The probability of occurrence may range anywhere from 0.1 to 0.9
The severity of the consequences due to a risk may be as high as system crash or as low as system termination
The severity may or may not have financial consequences
  E.g., System crash in an airline reservation system has financial consequences whereas failure of an email server in a university environment may not have severe financial problems

## Slide 6: Categories of risks
Project risks
  Project schedule changes
    A team member quits
    A team member is reassigned to another project
    A resource becomes unavailable
    Budget cut
Technical risks
  Major design errors
    Requirements and/or design must be revised before continuing
  Incompatibility or interoperability problems with external resources such as databases
  Failure of a tool used for development

## Slide 7: Categories of risks (continued)
Business risks
  Market slips; no one is currently interested in buying the product
  Product no longer fits into the business strategy of the organization
  Marketing team not trained to sell this product
  Change in management; new management does not support this product
  Change in organizational structure, staff and/or budget re-allocation
  Unrealistic delivery date
    Wrong estimation of project deadline

## Slide 8: Risk identification in a US Air Force project
Risks | Category | Probability | Impact
More users than planned | Product size | 30% | 3
Less market value | Business risk | 40% | 2
Deadline shortened | Business risk | 70% | 2
Budget cut | Business risk | 30% | 1
Less reuse than planned | Technology risk | 25% | 4
Customer changes the requirements | Product, technology and business risk | 75% | 1
Impact values: 1 – catastrophic 2 – critical 3 – marginal 4 - negligible

## Slide 9: Impact of risk management on cost
Risk management involves additional cost
What if the risks do not occur?
  Remember that they are probabilistic events
  Do the time and resources spent on risk management become a waste?
  An analogy:
    insurance company and insurance policies
Due to the severance of the consequences, risks must be handled, not ignored

## Slide 10: Impact of risk management on cost (continued)
Quote from the book The Project Manager’s Guide to Software Engineering’s Best Practices by M.J. Christensen and R.H. Thayer, IEEE Computer Society Press, 2001.
  Sometimes risk management is viewed as a bad influence on the development team. Any individual who identifies risk (large or small) may be deemed a “troublemaker” and is often shunted aside or ignored by both management and other team members.
  Software project management deals with risks common to all software projects, while risk management focuses on unique threats to a specific project that might affect the development, delivery and maintenance of the product

## Slide 11: Risk management (continued)
Involves
  Identification of risks
  Assessment of risks
    Probability of occurrence
    Severity of consequences
  Planning to incorporate remedial actions
  Monitoring the occurrences of risks and execution of remedial actions
  Revising risks continuously during development

## Slide 12: Risk management (continued)
Risk management
Risk assessment
Risk control
Risk identification
Risk analysis
Risk prioritization
Risk management plan
Risk resolution
Risk monitoring

## Slide 13: Risk identification
Risks can be identified by
  Looking at the events happened in previous projects
    Use projects database
  Literature surveys, opinions from others, …
  Think about “what if …” situations
  Some risks are evident
    Third-party tool or software integration
    Remote access
    No backup systems

## Slide 14: Risk categorization
Risks can be identified in various levels
Risks at requirements level
  Requirements are not well-defined
    Requirements analysis is not done properly or analysis ignored due to time constraints, business policies etc.
  Requirements are derived from another project; re-engineering project
    Environment and users changed
  Requirements are derived from sources other than customers (literature survey, market analysis, ...)
  Unjustifiable assumptions
  What can you say about risks if there is no requirements document?

## Slide 15: Risk categorization (continued)
Risks at the design level
  Design functionalities do not match with requirements
    Design analysis not performed or ignored
  Design tools, techniques, notations and algorithms limit or constrain functionalities that are not exposed at requirements level
    E.g., a graph processing algorithm will not be applicable to the functionality that is being designed
  Selection of improper or incompatible external software

## Slide 16: Risk categorization (continued)
Risks at the programming level
  Hardware failure
  System crash and loosing entire program
  No backups or long gaps between backups
  Programming standards or organizational programming principles not strictly followed
  Incompatibility of interfaces (internal and external)

## Slide 17: Risk categorization (continued)
Schedule risks
  Improper planning, often due to manual ad-hoc schedule preparation
Cost risks
  Poor cost estimation, often due to choosing inappropriate cost estimation model
  COCOMO II is developed to address cost and schedule risks
        Christenen and Thayer, 2001

## Slide 18: Risk analysis
Identify prob(r) , the probability of occurrence of each risk r.
Identify loss(r) , the cost of the consequences due to the risk r.
  Loss may identified in different units (time delay, financial cost, resources, …)
Compute re(r) , the risk exposure factor for the risk which is the effective loss due to r.
  re(r) = prob(r) * loss(r)

## Slide 19: Risk analysis – impact of numerical calculations
Often, it may not be possible to exactly calculate the value for risk exposure
  Depends on numerical values of prob(r) and loss(r)
Sometimes a comparative or relative values may be used
  Examples
    Low probability with very high loss
    Medium probability with medium loss

## Slide 20: Risk prioritization
Arrange the risks in certain priority order
  Depending on the risk exposure value
    Most common prioritization method
  Depending on the loss
  Depending on the probability of occurrence
  Depending on the category
    May be divided into categories first and then prioritize within each category
Only those risks that can be managed within the budget limitations will be taken into consideration
  The top N risks in the priority table

## Slide 21: Risk prioritization – non-numeric risk exposure values
How do you prioritize risks if we do not have numeric values for risk exposure?
Possible risk exposure values
  Low probability high loss Vs high probability low loss Vs medium probability medium loss
Project manager must decide based on past experience and other factors
  Possibly based on organizational/business policies
  Some extrapolation may be necessary

## Slide 22: Risk management planning
Once risks are identified and prioritized, project manager will know or at least will be informed by higher management which risks must be handled
  Typically the top N risks in the priority table
Design solutions to solve risk problems
  Find out additional resources (including man power)
  Perform cost analysis
  Plan for intermediate checking of risk factors
    Risk monitoring and tracking
  Plan for re-evaluation of risks at various stages
  Plan for recording risk management activities

## Slide 23: Some suggested risk management plans
Plan for extra project time
  about 10 to 20% extra time is common for most projects
Maintain extra or additional resources
Plan for training at any time
Plan to rotate team members with different tasks/roles
Perform simulations whenever possible and analyze the solutions
Plan for additional testing and more review sessions

## Slide 24: Sample risk management plan
Risk | Prob | Loss | Exposure | Plan
Tools / technology used for the first time | 0.9 | 3 | 2.7 | Plan for training ahead of time; escalate schedule; ask for experts help
Project members leave / quit | 0.3 | 7 | 2.1 | Keep additional man power; let everyone know about everything in the project
Remote access of a resource (may be a remote database) | 0.15 | 8 | 1.2 | Keep duplicate files; keep frequent backups; escalate schedule

## Slide 25: Risk monitoring and tracking
Risks of high priority at one time may not be even risks anymore
  Example:
    New technology introduced into product development line
      Changes after the team members get experience
    Remote data access has now a permanent connection or a duplicate copy
    Stability of project teams (no member leaves the organization because of other commitments!!)

## Slide 26: Risk monitoring and tracking (continued)
Risks factors must be continuously monitored
  Check how many times a remote access fails
  Check how often a team size changes
Reassess risk exposure values at various stages during development
  Probability may change
Record all these information for future use

## Slide 27: An exercise
Identify possible risks for the following problem; also identify their categories, probabilities, consequences and management (your) decisions:
  You are asked to develop a billing system for a small clinic. The system must connect to various insurance companies, credit card companies and policy maintainers. Patients are expected to pay for their bill or must have a proof that they are adequately covered, before they leave the clinic.

## Slide 28: Another exercise
Identify possible risks for the following problem; also identify their categories, probabilities, consequences and management (your) decisions:
  In this project you are asked to develop a software product for a law-firm. The company stores customer records, court hearing documents all online. Only the law-firm employees (lawyers and staff) can access the materials but they should be able to access it from any place (for example, when they are in the court room).