## User Story
S. No | As a <<type of user>> | I want <<some goal>> | so that <<reason>> | Date introduced | Date considered for implementation | Developer Responsible | Current Status
1 | Physician | Know the work flow of EMR system | Make sure the business logic of the whole system is correct | 2015-02-06 | 2015-02-10 | Yufan Xue | Finished
2 | Physician | Login | physician can access the system and perform admin related tasks | 2015-02-10 | 2015-02-15 | Yufan Xue | Finished
3 | Physician | View patients | View patients | 2015-02-16 | 2015-02-20 | Yufan Xue | Finished
4 | Physician | View an EMR | By default, a physician can search view all EMRs of his/her patients. To view the EMR of another patient, the physician should have been given access rights by the primary care of the corresponding physician. | 2015-02-22 | 2015-02-28 | Yufan Xue | Finished
5 | Physician | Add an EMR | Pysician can add an EMR for a patient There should be at most only one EMR per patient. A physician can create an EMR for a patient if and only if the physician is the primary care of the patient. | 2015-02-22 | 2015-03-03 | Yufan Xue | Finished
6 | Physician | Search an EMR | Search an EMR or a collection of EMRs. | 2015-03-03 | 2015-03-06 | Yufan Xue | Finished
7 | Physician | Update EMR of a patient | Updating an EMR should not modify or delete any existing transcription. Instead, it may change the patient's preferences | 2015-02-22 | 2015-03-03 | Yufan Xue | Finished
8 | Physician | Add a new trasncription | Add a new trasncription when a patient sees a physician | 2015-03-03 | 2015-03-10 | Yufan Xue | Finished
9 | Physician | View an trasncription | View transcription | 2015-03-03 | 2015-03-06 | Yufan Xue | Finished
10 | Physician | Search drug | Pysican input drug informations such as name and cemercial names to search drug, and system will display drug lists which are matching querying. | 2015-03-03 | 2015-03-10 | Yufan Xue | Finished
11 | Physician | Add a new prescription | Add a new prescription | 2015-03-03 | 2015-03-10 | Yufan Xue | Finished
12 | Physician | View a prescription | View a prescription | 2015-03-03 | 2015-03-06 | Yufan Xue | Finished
13 | Physician | Search physician | primary care physician wants to add other physician for patient, so he can search other physician based on his requirement. | 2015-03-03 | 2015-03-06 | Yufan Xue | Finished
14 | Physician | Add acceess rights for another physician to a patient's EMR | The physician may choose to give permanent access right or temporary access right. In the latter case, the date and time at which the access right expires must also be indicated. | 2015-03-03 | 2015-03-10 | Yufan Xue | Finished
15 | Physician | Delete access rights for another physician to a patient's EMR | The physician may choose to give permanent access right or temporary access right. In the latter case, the date and time at which the access right expires must also be indicated. | 2015-03-03 | 2015-03-10 | Yufan Xue | Finished
16 | Admin | Create an accounts for physicians | There must be an administrator (or administrators) for the EMR component who will create the accounts for the physicians. |  |  |  | Not Started
17 | Admin | Delete an account for physicians | An administrator can only add or delete an account for a physician or for another administrator. |  |  |  | Not Started
This color meas what we have done for last demo
This color means what we did for this demo

## Sprints
S.No. | User Story index | Task | Date introduced | Date considered for implementation | Date completed | Developer responsible for | Current Status
1 | 1 | Look up Medical Record template, find out what Medical Record look like | 2015-02-01 | 2015-02-02 | 2015-02-02 | Yufan xue | Finished
2 | 1 | Case study: a patient visit a physician, get the transcription from the physician | 2015-02-02 | 2015-02-03 | 2015-02-03 | Han chen | Finished
3 | 1 | Based on business logic, build the GUI | 2015-02-03 | 2015-02-09 | 2015-02-09 | Jingbo,Yufan,Han | Finished
4 | 2 | Set up the database | 2015-02-10 | 2015-02-10 | 2015-02-10 | Yufan xue | Finished
5 | 2 | Set up web interface,design the protocol(json data format) between the front end and server end | 2015-02-10 | 2015-02-13 | 2015-02-13 | Han chen | Finished
6 | 2 | Develop DB access methods for login component to check input password with database password | 2015-02-10 | 2015-02-13 | 2015-02-13 | Jingbo | Finished
7 | 2 | Develop GUI and front end control, the login.html and login.js | 2015-02-10 | 2015-02-13 | 2015-02-13 | Yufan xue | Finished
8 | 2 | Develop back end service,build web-API to tell front end whether user input valid password | 2015-02-10 | 2015-02-14 | 2015-02-14 | Yufan xue | Finished
9 | 2 | Integerate front end and back end | 2015-02-10 | 2015-02-15 | 2015-02-15 | Yufan xue | Finished
10 | 2 | Test login code for physician | 2015-02-15 | 2015-02-15 | 2015-02-15 | Han chen | Finished
11 | 3 | Set up the database,the patient table, the relation_patient_physician table | 2015-02-16 | 2015-02-16 | 2015-02-16 | Yufan xue | Finished
12 | 3 | Set up web interface,design the protocol(json data format) between the front end and server end | 2015-02-16 | 2015-02-18 | 2015-02-18 | Yufan xue | Finished
13 | 3 | Develop DB access methods, get patient list by physician Id,separate them by primary care and temporary care | 2015-02-17 | 2015-02-19 | 2015-02-19 | Han Chen | Finished
14 | 3 | Develop GUI and front end control, develop the patient list table use jQuery-datatable component | 2015-02-17 | 2015-02-19 | 2015-02-19 | JingBo | Finished
15 | 3 | Develop back end service,build web-API for physician to get his primary care patient list and temporary care patient list | 2015-02-17 | 2015-02-20 | 2015-02-20 | Han Chen | Finished
16 | 3 | Integerate front end and back end | 2015-02-20 | 2015-02-22 | 2015-02-22 | Yufan xue | Finished
17 | 3 | Test view patient code for physician | 2015-02-22 | 2015-02-24 | 2015-02-24 | Yufan xue | Finished
18 | 4 | Set up the database,the emr table | 2015-02-24 | 2015-02-25 | 2015-02-25 | yufan xue | Finished
19 | 4 | Set up patient web interface,design the protocol(json data format) between the front end and server end | 2015-02-25 | 2015-02-26 | 2015-02-26 | yufan xue | Finished
20 | 4 | Develop DB access methods,get the emr by patient id | 2015-02-25 | 2015-02-27 | 2015-02-27 | jingbo | Finished
21 | 4 | Develop GUI and front end control, generate the UI by request the server end data for patient role | 2015-02-27 | 2015-02-28 | 2015-02-28 | han chen | Finished
22 | 4 | Develop back end service,build web-API for physician to see the detail of one specified patient's emr content | 2015-02-27 | 2015-02-28 | 2015-02-28 | jingbo | Finished
23 | 4 | Integerate front end and back end | 2015-03-01 | 2015-03-02 | 2015-03-02 | yufan xue | Finished
24 | 4 | Test view EMR code for physician | 2015-03-02 | 2015-03-03 | 2015-03-03 | han chen | Finished
25 | 5 | Set up the database, the emr table has been created | 2015-02-24 | 2015-02-25 | 2015-02-25 | yufan xue | Finished
26 | 5 | Set up EMR web interface,design the protocol(json data format) between the front end and server end | 2015-02-25 | 2015-02-26 | 2015-02-26 | yufan xue | Finished
27 | 5 | Develop DB access methods, add a new emr for one patient | 2015-02-25 | 2015-02-27 | 2015-02-27 | han chen | Finished
28 | 5 | Develop GUI and front end control, build the UI for the create emr page named view_erm.html and view_emr.js to delivery data | 2015-02-27 | 2015-02-28 | 2015-02-28 | jingbo | Finished
29 | 5 | Develop back end service,build the web-API to get the post data from front end and insert into database for EMR instance | 2015-02-27 | 2015-02-28 | 2015-02-28 | han chen | Finished
30 | 5 | Integerate front end and back end | 2015-03-01 | 2015-03-02 | 2015-03-02 | yufan xue | Finished
31 | 5 | Test add EMR code for physician | 2015-03-02 | 2015-03-03 | 2015-03-03 | han chen | Finished
32 | 7 | Set up the database, the emr table has been created | 2015-02-24 | 2015-02-25 | 2015-02-25 | yufan xue | Finished
33 | 7 | Set up web interface,design the protocol(json data format) between the front end and server end | 2015-02-25 | 2015-02-26 | 2015-02-26 | yufan xue | Finished
34 | 7 | Develop DB access methods, change the basic information of an already existed emr for one patient | 2015-02-25 | 2015-02-27 | 2015-02-27 | jingbo | Finished
35 | 7 | Develop GUI(emr.html and emr.js) and front end controll | 2015-02-27 | 2015-02-28 | 2015-02-28 | han chen | Finished
36 | 7 | Develop back end service,build the web-API to get the post data from front end and update the database | 2015-02-27 | 2015-02-28 | 2015-02-28 | jingbo | Finished
37 | 7 | Integerate front end and back end | 2015-03-01 | 2015-03-02 | 2015-03-02 | yufan xue | Finished
38 | 7 | Test update EMR code for physician | 2015-03-02 | 2015-03-03 | 2015-03-03 | han chen | Finished
39 | 8 | Set up the database, the transcription table | 2015-03-03 | 2015-03-04 | 2015-03-04 | yufan xue | Finished
40 | 8 | Set up web interface,design the protocol(json data format) between the front end and server end | 2015-03-04 | 2015-03-06 | 2015-03-06 | yufan xue | Finished
41 | 8 | For the diagnostic test part, develop web-interface to provide name list for search input filed on the front end, develop front end part use jQuery to generate mutiple request to get the autocomplete dictionary | 2015-03-04 | 2015-03-09 | 2015-03-10 | yufan xue | Finished
42 | 8 | For surgery part, same as diagnostic part, develop both back end service and front end controll | 2015-03-04 | 2015-03-09 | 2015-03-10 | yufan xue | Finished
43 | 8 | For create a new transcription part, based on patientId,emrId, then generate a transcriptionID for the new transcription.Record the diagnostic test, surgery, abstraction and comment | 2015-03-04 | 2015-03-09 | 2015-03-10 | yufan xue | Finished
44 | 8 | Develop GUI and front end controll,use jQuery autocomplete to show the diagnostic test list and surgery list | 2015-03-04 | 2015-03-09 | 2015-03-10 | yufan xue | Finished
45 | 8 | Develop back end service,build the web-API to get the post data from front end and update the database | 2015-03-04 | 2015-03-10 | 2015-03-10 | yufan xue | Finished
46 | 8 | Integerate front end and back end | 2015-03-04 | 2015-03-10 | 2015-03-10 | yufan xue | Finished
47 | 8 | Test add transcription code of one emr | 2015-03-04 | 2015-03-10 | 2015-03-10 | yufan xue | Finished
48 | 9 | Set up the database, the transcription table has exsited | 2015-03-03 | 2015-03-04 | 2015-03-04 | yufan xue | Finished
49 | 9 | Set up web interface,design the protocol(json data format) between the front end and server end | 2015-03-04 | 2015-03-06 | 2015-03-06 | yufan xue | Finished
50 | 9 | Develop db access,read the transcription list belongs to one EMR | 2015-03-04 | 2015-03-06 | 2015-03-06 | yufan xue | Finished
51 | 9 | Develop GUI and front end control | 2015-03-04 | 2015-03-06 | 2015-03-06 | yufan xue | Finished
52 | 9 | Develop back end service,build the web-API to get the post data from front end and update the database | 2015-03-04 | 2015-03-10 | 2015-03-10 | yufan xue | Finished
53 | 9 | Integerate front end and back end | 2015-03-04 | 2015-03-10 | 2015-03-10 | yufan xue | Finished
54 | 9 | Test view transcription code of one emr | 2015-03-04 | 2015-03-10 | 2015-03-10 | yufan xue | Finished
55 | 10 | Set up the database, design the drug table | 2015-03-03 | 2015-03-04 | 2015-03-04 | yufan xue | Finished
56 | 10 | Set up web interface,design the protocol(json data format) between the front end and server end | 2015-03-04 | 2015-03-06 | 2015-03-06 | yufan xue | Finished
57 | 10 | Develop db access, based on what front end send, use sql like syntax get the drug name list | 2015-03-04 | 2015-03-06 | 2015-03-06 | yufan xue | Finished
58 | 10 | Develop GUI and front end control | 2015-03-04 | 2015-03-10 | 2015-03-10 | yufan xue | Finished
59 | 10 | Develop back end service,build the web-API to get the post data from front end and update the database | 2015-03-04 | 2015-03-10 | 2015-03-10 | yufan xue | Finished
60 | 10 | Integerate front end and back end | 2015-03-04 | 2015-03-10 | 2015-03-10 | yufan xue | Finished
61 | 10 | Test search drug code for emr | 2015-03-04 | 2015-03-10 | 2015-03-10 | yufan xue | Finished
62 | 11 | Set up the database, the prescription table | 2015-03-03 | 2015-03-04 | 2015-03-04 | yufan xue | Finished
63 | 11 | Set up web interface,design the protocol(json data format) between the front end and server end | 2015-03-04 | 2015-03-06 | 2015-03-06 | yufan xue | Finished
64 | 11 | Develop db access,generate a new prescription with the transcriptionID and assign a new prescriptionID for the new prescription | 2015-03-04 | 2015-03-06 | 2015-03-06 | yufan xue | Finished
65 | 11 | Develop GUI and front end control | 2015-03-04 | 2015-03-09 | 2015-03-10 | yufan xue | Finished
66 | 11 | Develop back end service,build the web-API to get the post data from front end and update the database | 2015-03-04 | 2015-03-09 | 2015-03-10 | yufan xue | Finished
67 | 11 | Integerate front end and back end | 2015-03-04 | 2015-03-10 | 2015-03-10 | yufan xue | Finished
68 | 11 | Test add new prescription code for transcription | 2015-03-04 | 2015-03-10 | 2015-03-10 | yufan xue | Finished
69 | 12 | Set up the database, the prescription table has existed | 2015-03-03 | 2015-03-04 | 2015-03-04 | yufan xue | Finished
70 | 12 | Set up web interface,design the protocol(json data format) between the front end and server end | 2015-03-04 | 2015-03-06 | 2015-03-06 | yufan xue | Finished
71 | 12 | Develop db access, get the prescription list belongs to one transcription | 2015-03-04 | 2015-03-06 | 2015-03-06 | yufan xue | Finished
72 | 12 | Develop GUI and front end control | 2015-03-04 | 2015-03-09 | 2015-03-10 | yufan xue | Finished
73 | 12 | Develop back end service,build the web-API to get the post data from front end and update the database | 2015-03-04 | 2015-03-10 | 2015-03-10 | yufan xue | Finished
74 | 12 | Integerate front end and back end | 2015-03-04 | 2015-03-10 | 2015-03-10 | yufan xue | Finished
75 | 12 | Test view prescription code for one transcription | 2015-03-04 | 2015-03-10 | 2015-03-10 | yufan xue | Finished
76 | 13 | Set up the database, the physician table has existed | 2015-03-03 | 2015-03-04 | 2015-03-04 | jingbo chu | Finished
77 | 13 | Set up web interface,design the protocol(json data format) between the front end and server end | 2015-03-04 | 2015-03-06 | 2015-03-06 | jingbo chu | Finished
78 | 13 | Develop db access, based on what front end send, use sql like syntax to get the physician name list | 2015-03-04 | 2015-03-06 | 2015-03-06 | jingbo chu | Finished
79 | 13 | Develop GUI and front end control | 2015-03-04 | 2015-03-10 | 2015-03-10 | jingbo chu | Finished
80 | 13 | Develop back end service,build the web-API to get the post data from front end and update the database | 2015-03-04 | 2015-03-10 | 2015-03-10 | jingbo chu | Finished
81 | 13 | Integerate front end and back end | 2015-03-04 | 2015-03-10 | 2015-03-10 | jingbo chu | Finished
82 | 13 | Test search physician | 2015-03-04 | 2015-03-10 | 2015-03-10 | jingbo chu | Finished
83 | 14 | Set up the database, the relation_physician_patient table has existed | 2015-03-03 | 2015-03-04 | 2015-03-04 | jingbo chu | Finished
84 | 14 | Set up web interface,design the protocol(json data format) between the front end and server end | 2015-03-04 | 2015-03-06 | 2015-03-06 | jingbo chu | Finished
85 | 14 | Develop db access, add a new temproray relation between one patient and physician, also, specified the access level(read, read/write) | 2015-03-04 | 2015-03-06 |  | jingbo chu | In Progessing
86 | 14 | Develop GUI and front end control | 2015-03-04 | 2015-03-10 |  | jingbo chu | In Progessing
87 | 14 | Develop back end service,build the web-API to get the post data from front end and update the database | 2015-03-04 | 2015-03-10 |  | jingbo chu | In Progessing
88 | 14 | Integerate front end and back end | 2015-03-04 | 2015-03-10 |  | jingbo chu | In Progessing
89 | 14 | Test add acceess rights for another physician to a patient's EMR | 2015-03-04 | 2015-03-10 |  | jingbo chu | In Progessing
90 | 15 | Set up the database, the relation_physician_patient table has existed | 2015-03-03 | 2015-03-04 | 2015-03-04 | jingbo chu | Finished
91 | 15 | Set up web interface,design the protocol(json data format) between the front end and server end | 2015-03-04 | 2015-03-06 | 2015-03-06 | jingbo chu | Finished
92 | 15 | Develop db access, delete one temproray relation by the relation id | 2015-03-04 | 2015-03-06 |  | jingbo chu | In Progessing
93 | 15 | Develop GUI and front end control | 2015-03-04 | 2015-03-10 |  | jingbo chu | In Progessing
94 | 15 | Develop back end service,build the web-API to get the post data from front end and update the database | 2015-03-04 | 2015-03-10 |  | jingbo chu | In Progessing
95 | 15 | Integerate front end and back end | 2015-03-04 | 2015-03-10 |  | jingbo chu | In Progessing
96 | 15 | Test delete acceess rights for another physician to a patient's EMR | 2015-03-04 | 2015-03-10 |  | jingbo chu | In Progessing
This color meas what we have done for last demo
This color means what we did for this demo