## User Story
S. No | As a <<type of user>> | I want <<some goal>> | so that <<reason>> | Date introduced | Date considered for implementation | Developer Responsible | Current Status
1 | Physician | Know the work flow of EMR system | Make sure the business logic of the whole system is correct | 2015-02-06 | 2015-02-10 | Yufan Xue | Finished
2 | Physician | Login | physician can access the system and perform admin related tasks | 2015-02-10 | 2015-02-15 | Yufan Xue | Finished
3 | Physician | View patients | View patients | 2015-02-16 | 2015-02-20 | Yufan Xue | Finished
4 | Physician | View an EMR | By default, a physician can search view all EMRs of his/her patients. To view the EMR of another patient, the physician should have been given access rights by the primary care of the corresponding physician. | 2015-02-22 | 2015-02-28 | Yufan Xue | Finished
5 | Physician | Add an EMR | Pysician can add an EMR for a patient There should be at most only one EMR per patient. A physician can create an EMR for a patient if and only if the physician is the primary care of the patient. | 2015-02-22 | 2015-03-03 | Yufan Xue | Finished
6 | Physician | Search an EMR | Search an EMR or a collection of EMRs. | 2015-03-03 | 2015-03-06 | Yufan Xue | Finished
7 | Physician | Update EMR of a patient | Updating an EMR should not modify or delete any existing transcription. Instead, it may change the patient's preferences | 2015-02-22 | 2015-03-03 | Yufan Xue | Finished
8 | Physician | Add a new trasncription | Add a new trasncription when a patient sees a physician | 2015-03-03 | 2015-03-10 | Yufan Xue | Finished
9 | Physician | View an trasncription | View transcription | 2015-03-03 | 2015-03-06 | Yufan Xue | Finished
10 | Physician | Search drug | Pysican input drug informations such as name and cemercial names to search drug, and system will display drug lists which are matching querying. | 2015-03-03 | 2015-03-10 | Yufan Xue | Finished
11 | Physician | Add a new prescription | Add a new prescription | 2015-03-03 | 2015-03-10 | Yufan Xue | Finished
12 | Physician | View a prescription | View a prescription | 2015-03-03 | 2015-03-06 | Yufan Xue | Finished
13 | Physician | Search physician | primary care physician wants to add other physician for patient, so he can search other physician based on his requirement. | 2015-03-03 | 2015-03-06 | Yufan Xue | Finished
14 | Physician | Add acceess rights for another physician to a patient's EMR | The physician may choose to give permanent access right or temporary access right. In the latter case, the date and time at which the access right expires must also be indicated. | 2015-03-03 | 2015-03-10 | Yufan Xue | Finished
15 | Physician | Delete access rights for another physician to a patient's EMR | The physician may choose to give permanent access right or temporary access right. In the latter case, the date and time at which the access right expires must also be indicated. | 2015-03-03 | 2015-03-10 | Yufan Xue | Finished
16 | Admin | retrieve physicans and patients | There must be an administrator (or administrators) for the EMR component who can retrieve all physicians and patients | 2015-03-24 | 2015-03-31 | Jingbo | Finished
17 | Admin | retrieve medical staff and admins | There must be an administrator (or administrators) for the EMR component who can retrieve all medical staff and admins | 2015-03-24 | 2015-03-31 | Jingbo | Finished
18 | Admin | manage(CRUD) medical staff and physician relation | adminstrators can create, retrieve, update and delete a relation between medical staff and physician | 2015-03-24 | 2015-04-08 | Jingbo | On process
19 | Admin | manage(CRUD) patient and physician relation | adminstrators can create, retrieve, update and delete a relation between patient and physician | 2015-03-24 | 2015-04-08 | Jingbo | On process
20 | Admin | manage(CRUD) physician and department relation | One physician only can belong to one department but one department can have many physicians inside | 2015-03-24 | 2015-03-31 | Han | Finished
21 | Admin | manage(CRUD) drug | The durg table structure only contains drug_id and drug_name so far because we still need to talk about this with pharmacy group. Therefore so far administrator only can manage drug_names | 2015-03-24 | 2015-03-31 | Han | Finished
22 | Admin | manage(CRUD) diagnostic test | adminstrator can create, retrieve, update and delete diagonistic test | 2015-03-24 | 2015-03-31 | Jingbo | Finished
23 | Admin | manage(CRUD) surgery | According to requirement, EMR system administrator has right to modify the surgery table structure and manage any entry of this table | 2015-03-24 | 2015-03-31 | Han | Finished
24 | Admin | Login function implementation | Admin has to login to the system to do those operations | 2015-03-24 | 2015-03-29 | Han | Finished
25 | A medical staff | get the same access right of patients from associated physicians | A medical staff member associated with a physician will have the same access rights to the EMRs that the physician has. If the physician grants access rights to another physician, then the medical staff members associated with the other physician will automatically inherit the same rights. The same is true when the access rights are cancelled. | 2015-03-24 | 2015-03-29 | Yufan Xue | Finished
26 | A medical staff | create transcription |  | 2015-03-24 | 2015-03-29 | Yufan Xue | Finished
27 | A medical staff | assign limited diagnostic test | There are several simple duties such as cleaning a wound, putting a needle, checking blood pressure and temperature etc. | 2015-03-24 | 2015-03-29 | Yufan Xue | Finished
29 | A medical staff | create prescription |  | 2015-03-24 | 2015-03-29 | Yufan Xue | Finished
30 | A medical staff | assign limited medicine | You must work with the pharmacy group to identify which medicines can be prescribed by a medical staff member. In the prescription, both the medical staff member's information and the associated physician's information must be included. However, if a physician is writing the prescription, only the physician's information will be included. | 2015-03-24 | 2015-03-29 | Yufan Xue | Finished
31 | Admin | Search physician by name before adding him to department | Before adding an existing physician to department, admin should be able to search the physician by name inputted. Therefore there will be a name list corresponding to all searching result shown in table and admin can choose who he wants to add. If some of those physician has already belonged to a department, the table should show which department who belongs to. | 2015-03-31 | 2015-04-10 | Han Chen | On process
32 | Admin | Display physicians' specialties instead of birthdays | Birthdays are very private information in terms of personal aspect. For general we don't need birthday but specialty in this situation. | 2015-03-31 | 2015-04-11 | Han Chen | On process
33 | Admin | Search physician name before add primary relation | when the admin adds a primary relation for the certain physician, admin should be able to search the physician by name inputted. Some physician personal information should be shown in table and admin can choose who he wants to add. | 2015-03-31 | 2015-04-12 | Jingbo Chu | On process
34 | Admin | Search patient name before add primary relation | when the admin assigns a primary for a patient, admin should be able to search the patient by name inputted. Some patient personal information details should be shown in table and admin can choose who he wants to assign. If this patient has already been assigned, the warning message should be displayed. | 2015-03-31 | 2015-04-13 | Jingbo Chu | On process
35 | Admin | Splite physician, medical staff and patient names to two parts -- first name and last name | At the very beginning, we forgot to seperate names to first name and last name, which strugles us right now. Therefore we think it is about the time to deal with it. | 2015-03-31 | 2015-04-10 | Han Chen | On process
36 | System | get/send the data from adminnistrator component | patient/physician/relation | 2015-04-06 | 2015-04-20 | Yufan Xue | On process
37 | System | get/send the data from phamacy component | prescription | 2015-04-06 | 2015-04-20 | Yufan Xue | On process
38 | System | send the data to insurance component |  | 2015-04-06 | 2015-04-20 | Yufan Xue | On process
This color meas what we have done before last two demo
This color means what we did for last demo

## Sprints
S.No. | User Story index | Task | Date introduced | Date considered for implementation | Date completed | Developer responsible for | Current Status
1 | 1 | Look up Medical Record template, find out what Medical Record look like | 2015-02-01 | 2015-02-02 | 2015-02-02 | Yufan xue | Finished
2 | 1 | Case study: a patient visit a physician, get the transcription from the physician | 2015-02-02 | 2015-02-03 | 2015-02-03 | Han chen | Finished
3 | 1 | Based on business logic, build the GUI | 2015-02-03 | 2015-02-09 | 2015-02-09 | Jingbo,Yufan,Han | Finished
4 | 2 | Set up the database | 2015-02-10 | 2015-02-10 | 2015-02-10 | Yufan xue | Finished
5 | 2 | Set up web interface,design the protocol(json data format) between the front end and server end | 2015-02-10 | 2015-02-13 | 2015-02-13 | Han chen | Finished
6 | 2 | Develop DB access methods for login component to check input password with database password | 2015-02-10 | 2015-02-13 | 2015-02-13 | Jingbo | Finished
7 | 2 | Develop GUI and front end control, the login.html and login.js | 2015-02-10 | 2015-02-13 | 2015-02-13 | Yufan xue | Finished
8 | 2 | Develop back end service,build web-API to tell front end whether user input valid password | 2015-02-10 | 2015-02-14 | 2015-02-14 | Yufan xue | Finished
9 | 2 | Integerate front end and back end | 2015-02-10 | 2015-02-15 | 2015-02-15 | Yufan xue | Finished
10 | 2 | Test login code for physician | 2015-02-15 | 2015-02-15 | 2015-02-15 | Han chen | Finished
11 | 3 | Set up the database,the patient table, the relation_patient_physician table | 2015-02-16 | 2015-02-16 | 2015-02-16 | Yufan xue | Finished
12 | 3 | Set up web interface,design the protocol(json data format) between the front end and server end | 2015-02-16 | 2015-02-18 | 2015-02-18 | Yufan xue | Finished
13 | 3 | Develop DB access methods, get patient list by physician Id,separate them by primary care and temporary care | 2015-02-17 | 2015-02-19 | 2015-02-19 | Han Chen | Finished
14 | 3 | Develop GUI and front end control, develop the patient list table use jQuery-datatable component | 2015-02-17 | 2015-02-19 | 2015-02-19 | JingBo | Finished
15 | 3 | Develop back end service,build web-API for physician to get his primary care patient list and temporary care patient list | 2015-02-17 | 2015-02-20 | 2015-02-20 | Han Chen | Finished
16 | 3 | Integerate front end and back end | 2015-02-20 | 2015-02-22 | 2015-02-22 | Yufan xue | Finished
17 | 3 | Test view patient code for physician | 2015-02-22 | 2015-02-24 | 2015-02-24 | Yufan xue | Finished
18 | 4 | Set up the database,the emr table | 2015-02-24 | 2015-02-25 | 2015-02-25 | yufan xue | Finished
19 | 4 | Set up patient web interface,design the protocol(json data format) between the front end and server end | 2015-02-25 | 2015-02-26 | 2015-02-26 | yufan xue | Finished
20 | 4 | Develop DB access methods,get the emr by patient id | 2015-02-25 | 2015-02-27 | 2015-02-27 | jingbo | Finished
21 | 4 | Develop GUI and front end control, generate the UI by request the server end data for patient role | 2015-02-27 | 2015-02-28 | 2015-02-28 | han chen | Finished
22 | 4 | Develop back end service,build web-API for physician to see the detail of one specified patient's emr content | 2015-02-27 | 2015-02-28 | 2015-02-28 | jingbo | Finished
23 | 4 | Integerate front end and back end | 2015-03-01 | 2015-03-02 | 2015-03-02 | yufan xue | Finished
24 | 4 | Test view EMR code for physician | 2015-03-02 | 2015-03-03 | 2015-03-03 | han chen | Finished
25 | 5 | Set up the database, the emr table has been created | 2015-02-24 | 2015-02-25 | 2015-02-25 | yufan xue | Finished
26 | 5 | Set up EMR web interface,design the protocol(json data format) between the front end and server end | 2015-02-25 | 2015-02-26 | 2015-02-26 | yufan xue | Finished
27 | 5 | Develop DB access methods, add a new emr for one patient | 2015-02-25 | 2015-02-27 | 2015-02-27 | han chen | Finished
28 | 5 | Develop GUI and front end control, build the UI for the create emr page named view_erm.html and view_emr.js to delivery data | 2015-02-27 | 2015-02-28 | 2015-02-28 | jingbo | Finished
29 | 5 | Develop back end service,build the web-API to get the post data from front end and insert into database for EMR instance | 2015-02-27 | 2015-02-28 | 2015-02-28 | han chen | Finished
30 | 5 | Integerate front end and back end | 2015-03-01 | 2015-03-02 | 2015-03-02 | yufan xue | Finished
31 | 5 | Test add EMR code for physician | 2015-03-02 | 2015-03-03 | 2015-03-03 | han chen | Finished
32 | 7 | Set up the database, the emr table has been created | 2015-02-24 | 2015-02-25 | 2015-02-25 | yufan xue | Finished
33 | 7 | Set up web interface,design the protocol(json data format) between the front end and server end | 2015-02-25 | 2015-02-26 | 2015-02-26 | yufan xue | Finished
34 | 7 | Develop DB access methods, change the basic information of an already existed emr for one patient | 2015-02-25 | 2015-02-27 | 2015-02-27 | jingbo | Finished
35 | 7 | Develop GUI(emr.html and emr.js) and front end controll | 2015-02-27 | 2015-02-28 | 2015-02-28 | han chen | Finished
36 | 7 | Develop back end service,build the web-API to get the post data from front end and update the database | 2015-02-27 | 2015-02-28 | 2015-02-28 | jingbo | Finished
37 | 7 | Integerate front end and back end | 2015-03-01 | 2015-03-02 | 2015-03-02 | yufan xue | Finished
38 | 7 | Test update EMR code for physician | 2015-03-02 | 2015-03-03 | 2015-03-03 | han chen | Finished
39 | 8 | Set up the database, the transcription table | 2015-03-03 | 2015-03-04 | 2015-03-04 | yufan xue | Finished
40 | 8 | Set up web interface,design the protocol(json data format) between the front end and server end | 2015-03-04 | 2015-03-06 | 2015-03-06 | yufan xue | Finished
41 | 8 | For the diagnostic test part, develop web-interface to provide name list for search input filed on the front end, develop front end part use jQuery to generate mutiple request to get the autocomplete dictionary | 2015-03-04 | 2015-03-09 | 2015-03-10 | yufan xue | Finished
42 | 8 | For surgery part, same as diagnostic part, develop both back end service and front end controll | 2015-03-04 | 2015-03-09 | 2015-03-10 | yufan xue | Finished
43 | 8 | For create a new transcription part, based on patientId,emrId, then generate a transcriptionID for the new transcription.Record the diagnostic test, surgery, abstraction and comment | 2015-03-04 | 2015-03-09 | 2015-03-10 | yufan xue | Finished
44 | 8 | Develop GUI and front end controll,use jQuery autocomplete to show the diagnostic test list and surgery list | 2015-03-04 | 2015-03-09 | 2015-03-10 | yufan xue | Finished
45 | 8 | Develop back end service,build the web-API to get the post data from front end and update the database | 2015-03-04 | 2015-03-10 | 2015-03-10 | yufan xue | Finished
46 | 8 | Integerate front end and back end | 2015-03-04 | 2015-03-10 | 2015-03-10 | yufan xue | Finished
47 | 8 | Test add transcription code of one emr | 2015-03-04 | 2015-03-10 | 2015-03-10 | yufan xue | Finished
48 | 9 | Set up the database, the transcription table has exsited | 2015-03-03 | 2015-03-04 | 2015-03-04 | yufan xue | Finished
49 | 9 | Set up web interface,design the protocol(json data format) between the front end and server end | 2015-03-04 | 2015-03-06 | 2015-03-06 | yufan xue | Finished
50 | 9 | Develop db access,read the transcription list belongs to one EMR | 2015-03-04 | 2015-03-06 | 2015-03-06 | yufan xue | Finished
51 | 9 | Develop GUI and front end control | 2015-03-04 | 2015-03-06 | 2015-03-06 | yufan xue | Finished
52 | 9 | Develop back end service,build the web-API to get the post data from front end and update the database | 2015-03-04 | 2015-03-10 | 2015-03-10 | yufan xue | Finished
53 | 9 | Integerate front end and back end | 2015-03-04 | 2015-03-10 | 2015-03-10 | yufan xue | Finished
54 | 9 | Test view transcription code of one emr | 2015-03-04 | 2015-03-10 | 2015-03-10 | yufan xue | Finished
55 | 10 | Set up the database, design the drug table | 2015-03-03 | 2015-03-04 | 2015-03-04 | yufan xue | Finished
56 | 10 | Set up web interface,design the protocol(json data format) between the front end and server end | 2015-03-04 | 2015-03-06 | 2015-03-06 | yufan xue | Finished
57 | 10 | Develop db access, based on what front end send, use sql like syntax get the drug name list | 2015-03-04 | 2015-03-06 | 2015-03-06 | yufan xue | Finished
58 | 10 | Develop GUI and front end control | 2015-03-04 | 2015-03-10 | 2015-03-10 | yufan xue | Finished
59 | 10 | Develop back end service,build the web-API to get the post data from front end and update the database | 2015-03-04 | 2015-03-10 | 2015-03-10 | yufan xue | Finished
60 | 10 | Integerate front end and back end | 2015-03-04 | 2015-03-10 | 2015-03-10 | yufan xue | Finished
61 | 10 | Test search drug code for emr | 2015-03-04 | 2015-03-10 | 2015-03-10 | yufan xue | Finished
62 | 11 | Set up the database, the prescription table | 2015-03-03 | 2015-03-04 | 2015-03-04 | yufan xue | Finished
63 | 11 | Set up web interface,design the protocol(json data format) between the front end and server end | 2015-03-04 | 2015-03-06 | 2015-03-06 | yufan xue | Finished
64 | 11 | Develop db access,generate a new prescription with the transcriptionID and assign a new prescriptionID for the new prescription | 2015-03-04 | 2015-03-06 | 2015-03-06 | yufan xue | Finished
65 | 11 | Develop GUI and front end control | 2015-03-04 | 2015-03-09 | 2015-03-10 | yufan xue | Finished
66 | 11 | Develop back end service,build the web-API to get the post data from front end and update the database | 2015-03-04 | 2015-03-09 | 2015-03-10 | yufan xue | Finished
67 | 11 | Integerate front end and back end | 2015-03-04 | 2015-03-10 | 2015-03-10 | yufan xue | Finished
68 | 11 | Test add new prescription code for transcription | 2015-03-04 | 2015-03-10 | 2015-03-10 | yufan xue | Finished
69 | 12 | Set up the database, the prescription table has existed | 2015-03-03 | 2015-03-04 | 2015-03-04 | yufan xue | Finished
70 | 12 | Set up web interface,design the protocol(json data format) between the front end and server end | 2015-03-04 | 2015-03-06 | 2015-03-06 | yufan xue | Finished
71 | 12 | Develop db access, get the prescription list belongs to one transcription | 2015-03-04 | 2015-03-06 | 2015-03-06 | yufan xue | Finished
72 | 12 | Develop GUI and front end control | 2015-03-04 | 2015-03-09 | 2015-03-10 | yufan xue | Finished
73 | 12 | Develop back end service,build the web-API to get the post data from front end and update the database | 2015-03-04 | 2015-03-10 | 2015-03-10 | yufan xue | Finished
74 | 12 | Integerate front end and back end | 2015-03-04 | 2015-03-10 | 2015-03-10 | yufan xue | Finished
75 | 12 | Test view prescription code for one transcription | 2015-03-04 | 2015-03-10 | 2015-03-10 | yufan xue | Finished
76 | 13 | Set up the database, the physician table has existed | 2015-03-03 | 2015-03-04 | 2015-03-04 | jingbo chu | Finished
77 | 13 | Set up web interface,design the protocol(json data format) between the front end and server end | 2015-03-04 | 2015-03-06 | 2015-03-06 | jingbo chu | Finished
78 | 13 | Develop db access, based on what front end send, use sql like syntax to get the physician name list | 2015-03-04 | 2015-03-06 | 2015-03-06 | jingbo chu | Finished
79 | 13 | Develop GUI and front end control | 2015-03-04 | 2015-03-10 | 2015-03-10 | jingbo chu | Finished
80 | 13 | Develop back end service,build the web-API to get the post data from front end and update the database | 2015-03-04 | 2015-03-10 | 2015-03-10 | jingbo chu | Finished
81 | 13 | Integerate front end and back end | 2015-03-04 | 2015-03-10 | 2015-03-10 | jingbo chu | Finished
82 | 13 | Test search physician | 2015-03-04 | 2015-03-10 | 2015-03-10 | jingbo chu | Finished
83 | 14 | Set up the database, the relation_physician_patient table has existed | 2015-03-03 | 2015-03-04 | 2015-03-04 | jingbo chu | Finished
84 | 14 | Set up web interface,design the protocol(json data format) between the front end and server end | 2015-03-04 | 2015-03-06 | 2015-03-06 | jingbo chu | Finished
85 | 14 | Develop db access, add a new temproray relation between one patient and physician, also, specified the access level(read, read/write) | 2015-03-04 | 2015-03-06 | 2015-03-10 | jingbo chu | Finished
86 | 14 | Develop GUI and front end control | 2015-03-04 | 2015-03-10 | 2015-03-10 | jingbo chu | Finished
87 | 14 | Develop back end service,build the web-API to get the post data from front end and update the database | 2015-03-04 | 2015-03-10 | 2015-03-10 | jingbo chu | Finished
88 | 14 | Integerate front end and back end | 2015-03-04 | 2015-03-10 | 2015-03-10 | jingbo chu | Finished
89 | 14 | Test add acceess rights for another physician to a patient's EMR | 2015-03-04 | 2015-03-10 | 2015-03-10 | jingbo chu | Finished
90 | 15 | Set up the database, the relation_physician_patient table has existed | 2015-03-03 | 2015-03-04 | 2015-03-04 | jingbo chu | Finished
91 | 15 | Set up web interface,design the protocol(json data format) between the front end and server end | 2015-03-04 | 2015-03-06 | 2015-03-06 | jingbo chu | Finished
92 | 15 | Develop db access, delete one temproray relation by the relation id | 2015-03-04 | 2015-03-06 | 2015-03-10 | jingbo chu | Finished
93 | 15 | Develop GUI and front end control | 2015-03-04 | 2015-03-10 | 2015-03-10 | jingbo chu | Finished
94 | 15 | Develop back end service,build the web-API to get the post data from front end and update the database | 2015-03-04 | 2015-03-10 | 2015-03-10 | jingbo chu | Finished
95 | 15 | Integerate front end and back end | 2015-03-04 | 2015-03-10 | 2015-03-10 | jingbo chu | Finished
96 | 15 | Test delete acceess rights for another physician to a patient's EMR | 2015-03-04 | 2015-03-10 | 2015-03-10 | jingbo chu | Finished
| 25 | Set up the database, design the relation table to specify the relation between medical staff with physician | 2015-03-24 | 2015-03-27 |  | yufan xue | not started
| 25 | Set up web interface,design the protocol(json data format) between the front end and server end | 2015-03-24 | 2015-03-27 |  | yufan xue | not started
| 25 | Develop db access, get patient accessible list | 2015-03-24 | 2015-03-27 |  | yufan xue | not started
| 25 | Develop GUI and front end control | 2015-03-24 | 2015-03-27 |  | yufan xue | not started
| 25 | Develop back end service,build the web-API to reponse the accessible patient list | 2015-03-24 | 2015-03-27 |  | yufan xue | not started
| 25 | Integerate front end and back end | 2015-03-24 | 2015-03-27 |  | yufan xue | not started
| 25 | Test |  |  |  | yufan xue | not started
| 26 | Set up the database, change the transcription table, add filed to specify the person who create the transcription and the primary physician | 2015-03-24 | 2015-03-27 |  | yufan xue | not started
| 26 | Set up web interface,design the protocol(json data format) between the front end and server end | 2015-03-24 | 2015-03-27 |  | yufan xue | not started
| 26 | Change db access, update the insert sql | 2015-03-24 | 2015-03-27 |  | yufan xue | not started
| 26 | Change GUI and front end control | 2015-03-24 | 2015-03-27 |  | yufan xue | not started
| 26 | Change back end service,build the web-API to | 2015-03-24 | 2015-03-27 |  | yufan xue | not started
| 26 | Integerate front end and back end | 2015-03-24 | 2015-03-27 |  | yufan xue | not started
| 26 | Test |  |  |  | yufan xue | not started
| 27 | Set up the database, design the table to specify the limit diagnostic test that medicine staff can assign | 2015-03-24 | 2015-03-27 |  | yufan xue | not started
| 27 | Set up web interface,design the protocol(json data format) between the front end and server end | 2015-03-24 | 2015-03-27 |  | yufan xue | not started
| 27 | Develop db access, get the limit diagnositc test from db | 2015-03-24 | 2015-03-27 |  | yufan xue | not started
| 27 | Change GUI and front end control | 2015-03-24 | 2015-03-27 |  | yufan xue | not started
| 27 | Design back end service,build the web-API to show the limit diagnostic test | 2015-03-24 | 2015-03-27 |  | yufan xue | not started
| 27 | Integerate front end and back end | 2015-03-24 | 2015-03-27 |  | yufan xue | not started
| 27 | Test |  |  |  | yufan xue | not started
| 28 | Set up the database, design the table to specify the limit surgery that medicine staff can assign | 2015-03-24 | 2015-03-27 |  | yufan xue | not started
| 28 | Set up web interface,design the protocol(json data format) between the front end and server end | 2015-03-24 | 2015-03-27 |  | yufan xue | not started
| 28 | Develop db access, get the limit surgery from db | 2015-03-24 | 2015-03-27 |  | yufan xue | not started
| 28 | Change GUI and front end control | 2015-03-24 | 2015-03-27 |  | yufan xue | not started
| 28 | Design back end service,build the web-API to show the limit surgery | 2015-03-24 | 2015-03-27 |  | yufan xue | not started
| 28 | Integerate front end and back end | 2015-03-24 | 2015-03-27 |  | yufan xue | not started
| 28 | Test |  |  |  | yufan xue | not started
| 29 | Change the prescription table, record prescription creator
| 29 | Set up web interface,design the protocol(json data format) between the front end and server end
| 29 | Change the db access, insert prescription creator
| 29 | Change GUI and front end control
| 29 | Design back end service,build the web-API
| 29 | Integerate front end and back end
| 29 | Test
| 20 | Design database for department and the table structure for relation between physician and department | 2015-03-24 | 2015-03-30 | 2015-03-30 | han | finished
| 20 | Set up table and design the GUI of management for the department-physician relationship | 2015-03-24 | 2015-03-30 | 2015-03-30 | han | finished
| 20 | Implementing data access API based on the requirement designed earlier | 2015-03-24 | 2015-03-30 | 2015-03-30 | han | finished
| 20 | Implement service layer and controller layer for being prepared for front page query | 2015-03-24 | 2015-03-30 | 2015-03-30 | han | finished
| 20 | Implement javascript and html based on the GUI designed earlier | 2015-03-24 | 2015-03-30 | 2015-03-30 | han | finished
| 20 | Test for each CRUD bussiness flow | 2015-03-24 | 2015-03-30 | 2015-03-30 | han | finished
| 20 | Debugging and testing repeatedly untill no bugs | 2015-03-24 | 2015-03-30 | 2015-03-30 | han | finished
| 20 | Combine this component with others and test it again | 2015-03-24 | 2015-03-30 | 2015-03-30 | han | finished
| 21 | Drug table has existed, design GUI for CRUD operation based on requirement | 2015-03-24 | 2015-03-30 | 2015-03-30 | han | finished
| 21 | Design and implement data access API and service API | 2015-03-24 | 2015-03-30 | 2015-03-30 | han | finished
| 21 | Design and implement controller layer API and Javascripts | 2015-03-24 | 2015-03-30 | 2015-03-30 | han | finished
| 21 | Modify GUI and javascripts | 2015-03-24 | 2015-03-30 | 2015-03-30 | han | finished
| 21 | Testing management(CRUD) operations based on requrement | 2015-03-24 | 2015-03-30 | 2015-03-30 | han | finished
| 21 | Debuging | 2015-03-24 | 2015-03-30 | 2015-03-30 | han | finished
| 21 | Combine this component with others and test it again | 2015-03-24 | 2015-03-30 | 2015-03-30 | han | finished
| 23 | Surgery table has existed, design GUI for CRUD operation based on requirement | 2015-03-24 | 2015-03-30 | 2015-03-30 | han | finished
| 23 | Design and implement data access API and service API | 2015-03-24 | 2015-03-30 | 2015-03-30 | han | finished
| 23 | Design and implement controller layer API and Javascripts | 2015-03-24 | 2015-03-30 | 2015-03-30 | han | finished
| 23 | Modify GUI and javascripts | 2015-03-24 | 2015-03-30 | 2015-03-30 | han | finished
| 23 | Testing management(CRUD) operations based on requrement | 2015-03-24 | 2015-03-30 | 2015-03-30 | han | finished
| 23 | Debuging | 2015-03-24 | 2015-03-30 | 2015-03-30 | han | finished
| 23 | Combine this component with others and test it again | 2015-03-24 | 2015-03-30 | 2015-03-30 | han | finished
| 24 | Admin account table has exists but there is no test data available. Prepared data and set up spring security configuration file to be prepared for implementation | 2015-03-24 | 2015-03-30 | 2015-03-30 | han | finished
| 24 | Design and implement data access API and service API | 2015-03-24 | 2015-03-30 | 2015-03-30 | han | finished
| 24 | Design and implement controller layer API and Javascripts | 2015-03-24 | 2015-03-30 | 2015-03-30 | han | finished
| 24 | Modify GUI and javascripts | 2015-03-24 | 2015-03-30 | 2015-03-30 | han | finished
| 24 | Testing Login operations based on requrement | 2015-03-24 | 2015-03-30 | 2015-03-30 | han | finished
| 24 | Debuging | 2015-03-24 | 2015-03-30 | 2015-03-30 | han | finished
| 24 | Combine this component with others and test it again | 2015-03-24 | 2015-03-30 | 2015-03-30 | han | finished
| 16 | patient and physician table has existed, design GUI for retrieve the patient list and the physician list based on requirement | 2015-03-24 | 2015-03-30 | 2015-03-30 | jingbo | finished
| 16 | Design and implement data access API and service API | 2015-03-24 | 2015-03-30 | 2015-03-30 | jingbo | finished
| 16 | Design and implement controller layer API and Javascripts | 2015-03-24 | 2015-03-30 | 2015-03-30 | jingbo | finished
| 16 | Modify GUI and javascripts | 2015-03-24 | 2015-03-30 | 2015-03-30 | jingbo | finished
| 16 | Testing retrieve lists based on requrement | 2015-03-24 | 2015-03-30 | 2015-03-30 | jingbo | finished
| 16 | Debuging | 2015-03-24 | 2015-03-30 | 2015-03-30 | jingbo | finished
| 16 | Combine this component with others and test it again | 2015-03-24 | 2015-03-30 | 2015-03-30 | jingbo | finished
| 17 | medical staff and admin table has existed, design GUI for retrieve the admin list and the medical staff list based on requirement | 2015-03-24 | 2015-03-30 | 2015-03-30 | jingbo | finished
| 17 | Design and implement data access API and service API | 2015-03-24 | 2015-03-30 | 2015-03-30 | jingbo | finished
| 17 | Design and implement controller layer API and Javascripts | 2015-03-24 | 2015-03-30 | 2015-03-30 | jingbo | finished
| 17 | Modify GUI and javascripts | 2015-03-24 | 2015-03-30 | 2015-03-30 | jingbo | finished
| 17 | Testing retrieve lists based on requrement | 2015-03-24 | 2015-03-30 | 2015-03-30 | jingbo | finished
| 17 | Debuging | 2015-03-24 | 2015-03-30 | 2015-03-30 | jingbo | finished
| 17 | Combine this component with others and test it again | 2015-03-24 | 2015-03-30 | 2015-03-30 | jingbo | finished
| 22 | Diagnostic test table has existed, design GUI for CRUD operation based on requirement | 2015-03-24 | 2015-03-30 | 2015-03-30 | jingbo | finished
| 22 | Design and implement data access API and service API | 2015-03-24 | 2015-03-30 | 2015-03-30 | jingbo | finished
| 22 | Design and implement controller layer API and Javascripts | 2015-03-24 | 2015-03-30 | 2015-03-30 | jingbo | finished
| 22 | Modify GUI and javascripts | 2015-03-24 | 2015-03-30 | 2015-03-30 | jingbo | finished
| 22 | Testing management(CRUD) operations based on requrement | 2015-03-24 | 2015-03-30 | 2015-03-30 | jingbo | finished
| 22 | Debuging | 2015-03-24 | 2015-03-30 | 2015-03-30 | jingbo | finished
| 22 | Combine this component with others and test it again | 2015-03-24 | 2015-03-30 | 2015-03-30 | jingbo | finished
| 18 | medical staff and physician relation table has not existed, design this table and GUI for CRUD operation based on requirement | 2015-03-24 | 2015-03-30 | 2015-04-06 | jingbo | finished
| 18 | Design and implement data access API and service API | 2015-03-24 | 2015-03-30 | 2015-04-07 | jingbo | finished
| 18 | Design and implement controller layer API and Javascripts | 2015-03-24 | 2015-03-30 |  | jingbo | on process
| 18 | Modify GUI and javascripts | 2015-03-25 | 2015-03-31 |  | jingbo | on process
| 18 | Testing management(CRUD) operations based on requrement | 2015-03-25 | 2015-03-31 |  | jingbo | on process
| 18 | Debuging | 2015-03-25 | 2015-03-31 |  | jingbo | on process
| 18 | Combine this component with others and test it again | 2015-03-26 | 2015-04-01 |  | jingbo | on process
| 19 | physician and patient relation table has existed, design GUI for CRUD operation based on requirement | 2015-03-24 | 2015-03-29 | 2015-04-06 | jingbo | finished
| 19 | Design and implement data access API and service API | 2015-03-24 | 2015-03-29 | 2015-04-07 | jingbo | finished
| 19 | Design and implement controller layer API and Javascripts | 2015-03-24 | 2015-03-30 |  | jingbo | on process
| 19 | Modify GUI and javascripts | 2015-03-25 | 2015-03-30 |  | jingbo | on process
| 19 | Testing management(CRUD) operations based on requrement | 2015-03-25 | 2015-03-30 |  | jingbo | on process
| 19 | Debuging | 2015-03-25 | 2015-03-30 |  | jingbo | on process
| 19 | Combine this component with others and test it again | 2015-03-26 | 2015-03-30 |  | jingbo | on process
| 31 | Desgin the manner to display the searching result | 2015-03-31 | 2015-04-10 |  | Han | on process
| 31 | Modify html and javascript code to satisfy requirement | 2015-03-31 | 2015-04-10 | 2015-04-07 | Han | finished
| 31 | Modify backend code to satisfy front page queries | 2015-03-31 | 2015-04-11 | 2015-04-06 | Han | finished
| 31 | Test and debug until there is no bugs | 2015-04-01 | 2015-04-11 |  | Han | on process
| 31 | Merge the codes with other components and test again | 2015-04-01 | 2015-04-12 |  | Han | on process
| 32 | Modify backend API to satisfy display changes | 2015-03-31 | 2015-04-11 | 2015-04-06 | Han | finished
| 32 | Modify html and javascript code to display the information correctly | 2015-03-31 | 2015-04-12 | 2015-04-07 | Han | finished
| 32 | Test and debug | 2015-03-31 | 2015-04-12 |  | Han | on process
| 32 | Merge the modified codes with other components together and test it again | 2015-04-01 | 2015-04-13 |  | Han | on process
| 32 | Merge all modified components together again to test and deploy the project to the server, and then test it again | 2015-04-01 | 2015-04-13 |  | Han | on process
| 33 | Modify physician-name search back-end method | 2015-03-30 | 2015-04-10 |  | Jingbo | on process
| 33 | Modify html and javascript code to show recommended physician name | 2015-03-31 | 2015-04-11 |  | Jingbo | on process
| 33 | Test and debug until there is no bugs | 2015-03-31 | 2015-04-11 |  | Jingbo | on process
| 33 |  | 2015-04-01 | 2015-04-12 |  | Jingbo | on process
| 33 | put call code together and publish code into git | 2015-04-01 | 2015-04-12 |  | Jingbo | on process
| 34 | Modify patient-name search back-end method | 2015-03-31 | 2015-04-10 |  | Jingbo | on process
| 34 | Modify html and javascript code to show recommended patient name | 2015-03-31 | 2015-04-11 |  | Jingbo | on process
| 34 | Unit test for back-end method | 2015-04-01 | 2015-04-12 |  | Jingbo | on process
| 34 | Test and debug until there is no bugs | 2015-04-01 | 2015-04-12 |  | Jingbo | on process
| 34 | put call code together and publish code into git | 2015-04-02 | 2015-04-13 |  | Jingbo | on process
|  | Create the interface for Administrator Component to add a new physician | 2015-04-03 | 2015-04-20 |  | yufan xue | on processing
|  | Create the interface for Administrator Component to delete a physician | 2015-04-04 | 2015-04-20 |  | yufan xue | on processing
|  | Create the interface for Administrator Component to change a physician | 2015-04-05 | 2015-04-20 |  | yufan xue | on processing
|  | Pull the drug data from Pharmacy Component | 2015-04-05 | 2015-04-20 |  | yufan xue | on processing
|  | Send prescription data to Pharmacy Component | 2015-04-06 | 2015-04-20 |  | yufan xue | on processing
|  | Send surgery data to Insurance Component | 2015-04-05 | 2015-04-20 |  | yufan xue | on processing
|  | Send diagonstic data to Insurance Component | 2015-04-06 | 2015-04-20 |  | yufan xue | on processing
|  | Send treatment data to Insurance Component | 2015-04-07 | 2015-04-20 |  | yufan xue | on processing
This color meas what we have done before last two demo
This color means what we did for last demo